## Istanbul Patch 2 Skiplist
File name | Target name | Type | Payload hash | Previous Hash Matches (Patch2) | Investigator | Investigation Status | Change Documentation | Outcome | Work Status
sys_security_acl_753fce20372201003e7d40ed9dbe5da8 | hr_case.work_notes | Access Control | -1152970791 | 0
sys_security_acl_fe2ecb56df303100dca6a5f59bf2631a | hr_case.requested_due_by | Access Control | -1528799860 | 0
sys_security_acl_8befe2580a0a0b4400046b909fd1ee76 | cmdb_ci | Access Control | -1611929914 | 0
sys_security_acl_4ea3c4f8df93210068c37a0d3df2633a | hr_case.company | Access Control | -1785065133 | 0
sys_security_acl_c6ebd251373201003e7d40ed9dbe5de8 | hr_case.department | Access Control | -1809393085 | 0
sys_security_acl_8fd994c3c0a801650085349761039ce7 | sys_report | Access Control | -1890599343 | 0
sysevent_email_template_adfe0cadc611227100ffab0a08978ef2 | change.itil.approve.role | Email Template | -1548566508 | 1
sysevent_email_template_adfe0cadc611227100ffab0a08978ef2 | change.itil.approve.role | Email Template | 641270785 | 1
sys_ui_list_dl_u_assignment_null | Assignment Data Lookup | List Layout | -1917725215 | 1
menu_item_1e05a66c081391006f7169ab4fb9555d | Approvals | Menu Item | 834938253 | 1
sysevent_email_action_2bd6f402c320020058bc3b251eba8fa9 | Capacity Subscription created | Notification | 1848241360 | 1
Note on H1: Adding Documentation really does help when we review all the changes. Please add a full description of changes

## Istanbul Patch 2 Need to Check
Description | Details | Who checked | Results | Bug Created? | Status | Fixer | Notes
HR ACLs | Check if new ACLs were inserted into HR Case record
HR Roles | Check is new roles were created and their inheritence. hr_agent now has hr_admin?
HR Restrict Query Business Rule | Make sure it behaves the same as before. We added approver permissions. Make sure that did not break. We also added a isInteractive check. Make sure that is still there
HR Module Menu | Check for new modules and renames of existing modules
Haas Survey | Check for new functionality
HR Assignment lookup rules | Check for new rules
Data Lookup Definitions | Check HR case and task definitions.
HR Factory + All sub scripts | Make sure that still works as before
HR Case and Task Table | Check for new fields
Dictionaries with our overrides | Check the dictionary over rides table for things made by us and compare if the dictionary has been changed
Check all field labels for incident and hr_case | They might have been renamed on us if we didn't change it
Check state choice list | Check the state choice list for Incident, HR Case, HR Task. Compare for overlaps with values. Check for changes in work in progress, completed, closed values
Check Data Policies | Check for Incident and HR new or altered OOB data policies
Incident Notifications | A few use the out of box template. Check those
Assignment Groups | Check for new assignment groups
HR Case/Task Flow | Check new flows where not inserted (Alters would be caught be skiplist)
HR Category Drop Down | Check for new or altered values
Knowledge Base | Check this still works...
Check HR Tables | Make sure our tables still stand the way we built them, light check
Check HR Catalog | Just make sure it's OK
Check HR Portal | Make sure its NOT active
Check HR Script includes | hr_case and hr_case_securitymanager (OOB versions we inherit from) script includes
Task Relationship Module | Check that still works as intended and didn't add new relationships
User Table Fields | Check for new fields
User Table Business Rules | Check for new rules
Check HR Workflows | Part of regression testing, but putting it here anyways. Maybe we can look at them as a developer and check too.
Check system property: glide.invalid_query.returns_no_rows | Make sure the system property is either not there or set to false. This will break our restrict query modifications on hr case. We add "or" conditions for rows only on some child tables.
LDAP Import | Just look at them. Make sure
Check shopping cart configuration | See if the shopping cart now shows up for HR/IT. We don't want it to
Check for new SLA | See if they added new SLAs for things like HR or IT
Lists V3 bug fixes | Check if the known bugs with lists v3 still exist
Validate API | Check if the built in SN table API still works properly
Review new Wishlist function | Review Wishlist Catalog Functionality with 'Wishlist' function

## Helsinki Patch 8 Skiplist
File name | Target name | Type | Payload hash | Previous Hash Matches (Patch2) | Investigator | Investigation Status | Change Documentation | Outcome | Work Status
sysevent_email_action_b2c45bcfc611227100d9025488a0cb3b | Approval Rejected | Notification | 700619821 | 0 | Bobby | Completed | We touched, but changes are minimal. Keep for now. | Keep | Complete
sysevent_email_action_b2c45bcfc611227100d9025488a0cb3b | Approval Rejected | Notification | 294163003 | 0 | Bobby | Completed | We touched, but changes are minimal. Keep for now. | Keep | Complete
menu_item_1e05a66c081391006f7169ab4fb9555d | Approvals | Menu Item | 834938253 | 0 | Mike | Completed | Name "My Approvals" vs. "Approvals" | Keep | Complete
sys_ui_list_dl_u_assignment_null | Assignment Data Lookup | List Layout | -1917725215 | 0 | Bobby | Completed | No changes in the update, revert | Revert | Complete
sysevent_email_action_2bd6f402c320020058bc3b251eba8fa9 | Capacity Subscription created | Notification | 2082950707 | 0 | Bobby | Completed | We haven't touched this, and subscriptions are oob. | Revert | Complete
sysevent_email_action_2bd6f402c320020058bc3b251eba8fa9 | Capacity Subscription created | Notification | 1848241360 | 0 | Bobby | Completed | We haven't touched this, and subscriptions are oob. | Revert | Complete
sysevent_email_action_f1ff45a1c0a8011b01f899e995dc7583 | Catalog Approval Rejected | Notification | -1232101736 | 0 | Bobby | Completed | UCBackup modification | Keep | Complete
sysevent_email_template_adfe0cadc611227100ffab0a08978ef2 | change.itil.approve.role | Email Template | -1548566508 | 0 | Bobby | Completed | Let's merge this one; they moved their inline mail script to an external mail script | Merge | Complete
sysevent_email_template_adfe0cadc611227100ffab0a08978ef2 | change.itil.approve.role | Email Template | 641270785 | 0 | Bobby | Completed | Our customization to approval email | Keep | Complete
Note on H1: Adding Documentation really does help when we review all the changes. Please add a full description of changes

## Helsinki Patch 8 Need to Check
Description | Details | Who checked | Results | Bug Created? | Status | Fixer | Notes
HR ACLs | Check if new ACLs were inserted into HR Case record | Justin | No Change |  | Completed |  | No change
HR Roles | Check is new roles were created and their inheritence. hr_agent now has hr_admin? | Justin | No Change |  | Completed |  | No change
HR Restrict Query Business Rule | Make sure it behaves the same as before. We added approver permissions. Make sure that did not break. We also added a isInteractive check. Make sure that is still there | Justin | No Change |  | Completed |  | No change
HR Module Menu | Check for new modules and renames of existing modules | Justin | No Change |  | Completed |  | No change
Haas Survey | Check for new functionality | Justin | No Change |  | Completed |  | No change
HR Assignment lookup rules | Check for new rules | Justin | No Change |  | Completed |  | No change
Data Lookup Definitions | Check HR case and task definitions. | Justin | No Change |  | Completed |  | No change
HR Factory + All sub scripts | Make sure that still works as before | Justin | No problem |  | Completed |  | Dead-Ish. Can ignore...
HR Case and Task Table | Check for new fields | Justin | No Change |  | Completed |  | No change
Dictionaries with our overrides | Check the dictionary over rides table for things made by us and compare if the dictionary has been changed | Justin | No Change |  | Completed |  | Does not look like there was a change
Check all field labels for incident and hr_case | They might have been renamed on us if we didn't change it | Justin | No problem |  | Completed |  | I do not know if there were changes, but as it stands there are no problems with the dictionary overrides
Check state choice list | Check the state choice list for Incident, HR Case, HR Task. Compare for overlaps with values. Check for changes in work in progress, completed, closed values | Justin | No Change |  | Completed |  | No change
Check Data Policies | Check for Incident and HR new or altered OOB data policies | Bobby | No Change |  | Completed |  | No active new data policies
Incident Notifications | A few use the out of box template. Check those | Justin | No Change |  | Completed |  | No change
Assignment Groups | Check for new assignment groups | Mike | No Change |  | Completed
HR Case/Task Flow | Check new flows where not inserted (Alters would be caught be skiplist) | Mike | No problem |  | Completed |  | Reviewed Published and Active Workflows, UC Backup Requests and HR Approval Workflow on TEST but not TEMP1
HR Category Drop Down | Check for new or altered values | Mike | No Change |  | Completed
Knowledge Base | Check this still works... | Bobby | No problem |  | Completed |  | Able to access KB, navigate to various articles as Test NoRoles
Check HR Tables | Make sure our tables still stand the way we built them, light check | Justin | No Change |  | Completed |  | No change
Check HR Catalog | Just make sure it's OK | Bobby | No problem |  | Completed |  | Able to access HR Catalog as Test NoRoles
Check HR Portal | Make sure its NOT active | Bobby | No Change |  | Completed |  | attempted to access, not available
Check HR Script includes | hr_case and hr_case_securitymanager (OOB versions we inherit from) script includes | Justin | No Change |  | Completed |  | No change
Task Relationship Module | Check that still works as intended and didn't add new relationships | Justin | No Change |  | Completed |  | No change
User Table Fields | Check for new fields | Mike | No Change |  | Completed
User Table Business Rules | Check for new rules | Justin | No Change |  | Completed |  | No change
Check HR Workflows | Part of regression testing, but putting it here anyways. Maybe we can look at them as a developer and check too. | Bobby | No Change |  | Completed
Check system property: glide.invalid_query.returns_no_rows | Make sure the system property is either not there or set to false. This will break our restrict query modifications on hr case. We add "or" conditions for rows only on some child tables. | Mike | No Change |  | Completed |  | Property does not exist in sys_properties table
LDAP Import | Just look at them. Make sure | Justin | No Change |  | Completed |  | No change
Check shopping cart configuration | See if the shopping cart now shows up for HR/IT. We don't want it to | Justin | No Change |  | Completed |  | No change
Check for new SLA | See if they added new SLAs for things like HR or IT | Bobby | No Change |  | Completed
Lists V3 bug fixes | Check if the known bugs with lists v3 still exist | Justin | No Change |  | Completed |  | Bug still exists
Validate API | Check if the built in SN table API still works properly